KẾ HOẠCH JIRA
WEBSITE ĐẶT VÉ MÁY BAY NỘI ĐỊA

SPRINT 2 → SPRINT 6 | 10/09/2026 – 30/12/2026

Tài liệu này được tái cấu trúc từ kế hoạch Sprint 2–6 hiện có. Sprint 1 đã hoàn thành và không đưa vào tài liệu. Cấu trúc Jira sử dụng: Epic → Story → Task → Subtask. Subtask chỉ tạo khi một Task đủ lớn và cần theo dõi độc lập; không tạo Subtask chỉ để liệt kê các thành phần kỹ thuật bên trong Task.

# 1. Quy ước Jira

| Cấp | Ý nghĩa | Ví dụ |
| --- | --- | --- |
| Epic | Nhóm chức năng lớn hoặc workstream lớn | Authentication & Account Management |
| Story | Một nghiệp vụ/chức năng có ý nghĩa hoàn chỉnh | Register; Login; Create Booking |
| Task | Công việc chính để hoàn thành Story | Thiết kế UI; Phát triển API; Unit Test |
| Subtask | Phần việc độc lập của một Task đủ lớn | Chỉ tạo khi cần theo dõi riêng |

Nguyên tắc: DTO, Service, Controller, Form, Validation, API Integration... là phạm vi bên trong Task nếu khối lượng chưa đủ lớn để cần tracking riêng. Không sử dụng một cột Subtask để ghi chú các nội dung này.

# 2. Phân công

| Người | Phụ trách chính | Vai trò |
| --- | --- | --- |
| Bình | Spring Boot, PostgreSQL, JPA/Hibernate, Spring Security/JWT, business logic, API, Backend Unit Test | Backend |
| Đức Anh | Angular, UI/UX, responsive, frontend validation, API integration, Frontend Test | Frontend |
| Cả hai | Integration Test, E2E, regression, code review, deployment verification, demo | Shared |

# 3. Epic tổng thể

| Epic | Tên Epic | Phạm vi chính |
| --- | --- | --- |
| EPIC-7 | Authentication & Account Management | Register, Login, Logout, Reset Password, Change Password, User Management, Profile |
| EPIC-8 | Authorization & Master Data Management | RBAC, Airline, City, Airport, Aircraft, Seat Configuration |
| EPIC-9 | Content & Promotion Management | Promotion, Voucher, News |
| EPIC-10 | Flight Management | Flight lifecycle |
| EPIC-11 | Flight Search & Fare Management | Flight Search, Fare Management |
| EPIC-12 | Seat Inventory Management | Flight Seat Inventory |
| EPIC-13 | Passenger & Booking Management | Passenger, Create Booking |
| EPIC-14 | Pricing & Seat Hold | Price Snapshot, Seat Selection, Seat Hold |
| EPIC-15 | Payment Management | Payment, Payment Retry |
| EPIC-16 | Booking Confirmation & E-Ticket | Booking Confirmation, PNR, E-Ticket |
| EPIC-17 | Booking Cancellation | Cancel Booking |
| EPIC-18 | Dashboard & Reporting | Dashboard |
| EPIC-19 | Integration, QA & Release | System Integration, Testing, UI/UX, Documentation, Deployment, Final Demo |

# Sprint 2 — Phase 1: Authentication, Account & Master Data

| Epic | Story | Task | Owner | Thời gian |
| --- | --- | --- | --- | --- |
| EPIC-7 | Register | Thiết kế UI Register | Đức Anh | 14/09 |
| EPIC-7 | Register | Phát triển Register API | Bình | 14/09 |
| EPIC-7 | Register | Phát triển Register Page & tích hợp API | Đức Anh | 14/09 |
| EPIC-7 | Register | Unit Test Register | Bình | 14/09 |
| EPIC-7 | Register | Integration Test Register | Cả hai | 14/09 |
| EPIC-7 | Login | Thiết kế UI Login | Đức Anh | 14/09 |
| EPIC-7 | Login | Phát triển Login API + JWT | Bình | 13/09–14/09 |
| EPIC-7 | Login | Phát triển Login Page | Đức Anh | 10/09–15/09 |
| EPIC-7 | Login | Unit Test Login/Auth | Bình | 12/09–14/09 |
| EPIC-7 | Login | Integration Test Login | Cả hai | 14/09 |
| EPIC-7 | Logout | Thiết kế màn hình Logout | Đức Anh | 15/09 |
| EPIC-7 | Logout | Phát triển Logout API/flow | Bình | 14/09–15/09 |
| EPIC-7 | Logout | Tích hợp Logout flow | Đức Anh | 15/09–16/09 |
| EPIC-7 | Reset Password | Thiết kế Reset Password UI | Đức Anh | 13/09–16/09 |
| EPIC-7 | Reset Password | Phát triển Reset Password API | Bình | 15/09–16/09 |
| EPIC-7 | Reset Password | Phát triển Reset Password flow | Đức Anh | 16/09 |
| EPIC-7 | Change Password | Thiết kế Change Password UI | Đức Anh | 17/09 |
| EPIC-7 | Change Password | Phát triển Change Password API | Bình | 17/09 |
| EPIC-7 | Change Password | Tích hợp Change Password flow | Đức Anh | 16/09–17/09 |
| EPIC-7 | Authentication | Unit Test Authentication services | Bình | 17/09–18/09 |
| EPIC-7 | Authentication | Integration Test Authentication | Cả hai | 19/09 |
| EPIC-7 | User Management | Thiết kế User Management UI | Đức Anh | 13/09–15/09 |
| EPIC-7 | User Management | Phát triển User Management API | Bình | 15/09–19/09 |
| EPIC-7 | User Management | Phát triển User Management Page | Đức Anh | 18/09–21/09 |
| EPIC-7 | User Management | Unit Test User service | Bình | 20/09–21/09 |
| EPIC-7 | User Management | Integration Test User Management | Cả hai | 22/09 |
| EPIC-7 | Profile | Thiết kế Profile UI | Đức Anh | 18/09–19/09 |
| EPIC-7 | Profile | Phát triển Profile API | Bình | 19/09–21/09 |
| EPIC-7 | Profile | Phát triển Profile Page & API integration | Đức Anh | 20/09–22/09 |
| EPIC-7 | Profile | Unit Test Profile | Bình | 21/09–22/09 |
| EPIC-7 | Profile | Integration Test Profile | Cả hai | 23/09 |
| EPIC-8 | RBAC | Thiết kế Role/Permission UI | Đức Anh | 20/09–21/09 |
| EPIC-8 | RBAC | Phát triển RBAC API | Bình | 20/09–23/09 |
| EPIC-8 | RBAC | Tích hợp RBAC Frontend | Đức Anh | 22/09–24/09 |
| EPIC-8 | RBAC | Unit Test Authorization | Bình | 23/09–24/09 |
| EPIC-8 | RBAC | Integration Test RBAC | Cả hai | 25/09 |
| EPIC-8 | Airline Management | Thiết kế UI Airline | Đức Anh | 18/09–20/09 |
| EPIC-8 | Airline Management | Phát triển Airline API | Bình | 18/09–22/09 |
| EPIC-8 | Airline Management | Phát triển Airline pages | Đức Anh | 20/09–23/09 |
| EPIC-8 | Airline Management | Unit Test Airline | Bình | 22/09–23/09 |
| EPIC-8 | City & Airport Management | Phát triển City/Airport API | Bình | 18/09–22/09 |
| EPIC-8 | City & Airport Management | Phát triển City/Airport pages | Đức Anh | 20/09–23/09 |
| EPIC-8 | City & Airport Management | Unit & Integration Test City/Airport | Cả hai | 24/09 |
| EPIC-8 | Aircraft & Seat Configuration | Thiết kế UI Aircraft & Seat Configuration | Đức Anh | 21/09–22/09 |
| EPIC-8 | Aircraft & Seat Configuration | Phát triển API Aircraft & Seat Configuration | Bình | 21/09–24/09 |
| EPIC-8 | Aircraft & Seat Configuration | Phát triển Angular pages | Đức Anh | 23/09–25/09 |
| EPIC-8 | Aircraft & Seat Configuration | Unit Test Configuration | Bình | 24/09–25/09 |
| EPIC-8 | Aircraft & Seat Configuration | Integration Test Configuration | Cả hai | 26/09 |
| EPIC-9 | Promotion Management | Thiết kế UI Promotion | Đức Anh | 22/09–24/09 |
| EPIC-9 | Promotion Management | Phát triển Promotion API | Bình | 22/09–25/09 |
| EPIC-9 | Promotion Management | Phát triển Promotion pages | Đức Anh | 24/09–26/09 |
| EPIC-9 | Promotion Management | Unit & Integration Test Promotion | Cả hai | 27/09 |
| EPIC-9 | Voucher Management | Thiết kế UI Voucher | Đức Anh | 22/09–24/09 |
| EPIC-9 | Voucher Management | Phát triển Voucher API | Bình | 22/09–25/09 |
| EPIC-9 | Voucher Management | Phát triển Voucher pages | Đức Anh | 24/09–26/09 |
| EPIC-9 | Voucher Management | Unit & Integration Test Voucher | Cả hai | 27/09 |
| EPIC-9 | News Management | Thiết kế UI News | Đức Anh | 22/09–24/09 |
| EPIC-9 | News Management | Phát triển News API | Bình | 22/09–25/09 |
| EPIC-9 | News Management | Phát triển News pages | Đức Anh | 24/09–26/09 |
| EPIC-9 | News Management | Unit & Integration Test News | Cả hai | 27/09 |

# Sprint 3 — Phase 2: Flight & Fare

| Epic | Story | Task | Owner | Thời gian |
| --- | --- | --- | --- | --- |
| EPIC-10 | Flight Management | Thiết kế UI Flight Management | Đức Anh | 28/09–30/09 |
| EPIC-10 | Flight Management | Phát triển Flight API & lifecycle | Bình | 28/09–03/10 |
| EPIC-10 | Flight Management | Phát triển Flight pages & API integration | Đức Anh | 01/10–05/10 |
| EPIC-10 | Flight Management | Unit Test Flight | Bình | 04/10–05/10 |
| EPIC-10 | Flight Management | Integration Test Flight | Cả hai | 06/10 |
| EPIC-11 | Flight Search | Thiết kế UI Search Result | Đức Anh | 04/10–06/10 |
| EPIC-11 | Flight Search | Phát triển Search API | Bình | 04/10–08/10 |
| EPIC-11 | Flight Search | Phát triển Search pages | Đức Anh | 06/10–09/10 |
| EPIC-11 | Flight Search | Unit Test Search | Bình | 08/10–09/10 |
| EPIC-11 | Flight Search | Integration Test Search | Cả hai | 10/10 |
| EPIC-11 | Fare Management | Thiết kế UI Fare & Baggage | Đức Anh | 08/10–10/10 |
| EPIC-11 | Fare Management | Phát triển Fare APIs | Bình | 08/10–13/10 |
| EPIC-11 | Fare Management | Phát triển Fare UI & integration | Đức Anh | 11/10–14/10 |
| EPIC-11 | Fare Management | Unit Test Fare | Bình | 13/10–14/10 |
| EPIC-11 | Fare Management | Integration Test Fare | Cả hai | 15/10 |
| EPIC-12 | Flight Seat Inventory | Thiết kế UI Seat Inventory | Đức Anh | 14/10–16/10 |
| EPIC-12 | Flight Seat Inventory | Phát triển Seat Inventory API | Bình | 14/10–18/10 |
| EPIC-12 | Flight Seat Inventory | Phát triển Seat Inventory UI | Đức Anh | 16/10–19/10 |
| EPIC-12 | Flight Seat Inventory | Unit Test Inventory | Bình | 18/10–19/10 |
| EPIC-12 | Flight Seat Inventory | Integration Test Inventory | Cả hai | 20/10 |
| EPIC-19 | Phase 2 Stabilization | Fix bug + hoàn thiện Phase 2 | Cả hai | 21/10–23/10 |
| EPIC-19 | Phase 2 Stabilization | Regression Test Phase 2 | Cả hai | 24/10–25/10 |

# Sprint 4 — Phase 3: Booking Core

| Epic | Story | Task | Owner | Thời gian |
| --- | --- | --- | --- | --- |
| EPIC-13 | Passenger | Thiết kế UI Passenger | Đức Anh | 26/10–28/10 |
| EPIC-13 | Passenger | Phát triển Passenger API | Bình | 26/10–30/10 |
| EPIC-13 | Passenger | Phát triển Passenger UI | Đức Anh | 29/10–01/11 |
| EPIC-13 | Passenger | Unit Test Passenger | Bình | 31/10–01/11 |
| EPIC-13 | Passenger | Integration Test Passenger | Cả hai | 02/11 |
| EPIC-13 | Create Booking | Thiết kế UI Booking | Đức Anh | 30/10–02/11 |
| EPIC-13 | Create Booking | Phát triển Create Booking API | Bình | 30/10–04/11 |
| EPIC-13 | Create Booking | Phát triển Booking Page | Đức Anh | 02/11–05/11 |
| EPIC-13 | Create Booking | Unit Test Booking | Bình | 04/11–05/11 |
| EPIC-13 | Create Booking | Integration Test Booking | Cả hai | 06/11 |
| EPIC-14 | Price Snapshot | Thiết kế UI Price Summary | Đức Anh | 04/11–05/11 |
| EPIC-14 | Price Snapshot | Phát triển Price Snapshot | Bình | 04/11–07/11 |
| EPIC-14 | Price Snapshot | Tích hợp Price Summary | Đức Anh | 06/11–08/11 |
| EPIC-14 | Price Snapshot | Unit Test Price Snapshot | Bình | 07/11–08/11 |
| EPIC-14 | Price Snapshot | Integration Test Price Snapshot | Cả hai | 09/11 |
| EPIC-14 | Seat Selection | Thiết kế UI Seat Selection | Đức Anh | 07/11–10/11 |
| EPIC-14 | Seat Selection | Phát triển Seat Selection UI & integration | Đức Anh | 10/11–13/11 |
| EPIC-14 | Seat Hold | Phát triển Seat Hold API | Bình | 07/11–12/11 |
| EPIC-14 | Seat Hold | Unit Test Seat Hold | Bình | 12/11–13/11 |
| EPIC-14 | Seat Hold | Integration Test Seat Hold | Cả hai | 14/11 |
| EPIC-19 | Booking Core Stabilization | Fix bug + hoàn thiện Booking Core | Cả hai | 15/11–19/11 |
| EPIC-19 | Booking Core Stabilization | Integration/Regression Test | Cả hai | 20/11–22/11 |

# Sprint 5 — Payment, Confirmation & E-Ticket

| Epic | Story | Task | Owner | Thời gian |
| --- | --- | --- | --- | --- |
| EPIC-15 | Payment | Thiết kế UI Payment | Đức Anh | 23/11–24/11 |
| EPIC-15 | Payment | Phát triển Payment API | Bình | 23/11–27/11 |
| EPIC-15 | Payment | Xử lý Payment và callback Gateway | Bình | 25/11–29/11 |
| EPIC-15 | Payment | Phát triển Payment Page & API integration | Đức Anh | 26/11–30/11 |
| EPIC-15 | Payment | Unit Test Payment | Bình | 29/11–30/11 |
| EPIC-15 | Payment | Integration Test Payment Gateway | Cả hai | 01/12 |
| EPIC-15 | Payment Retry | Thiết kế Retry Payment UI | Đức Anh | 30/11–01/12 |
| EPIC-15 | Payment Retry | Phát triển Retry Payment API | Bình | 30/11–02/12 |
| EPIC-15 | Payment Retry | Tích hợp Retry Flow | Đức Anh | 02/12–03/12 |
| EPIC-15 | Payment Retry | Unit Test Retry | Bình | 03/12 |
| EPIC-15 | Payment Retry | Integration Test Retry | Cả hai | 04/12 |
| EPIC-16 | Booking Confirmation | Thiết kế UI Confirmation | Đức Anh | 02/12–04/12 |
| EPIC-16 | Booking Confirmation | Phát triển Confirmation | Bình | 02/12–06/12 |
| EPIC-16 | Booking Confirmation | Phát triển Confirmation page | Đức Anh | 05/12–07/12 |
| EPIC-16 | Booking Confirmation | Unit Test Confirmation | Bình | 06/12–07/12 |
| EPIC-16 | Booking Confirmation | Integration Test Confirmation | Cả hai | 08/12 |
| EPIC-16 | PNR | Phát triển PNR generation | Bình | 02/12–06/12 |
| EPIC-16 | PNR | Unit Test PNR | Bình | 06/12–07/12 |
| EPIC-16 | E-Ticket | Thiết kế UI E-Ticket | Đức Anh | 02/12–04/12 |
| EPIC-16 | E-Ticket | Phát triển E-Ticket | Bình | 02/12–06/12 |
| EPIC-16 | E-Ticket | Phát triển E-Ticket page | Đức Anh | 05/12–07/12 |
| EPIC-16 | E-Ticket | Unit Test E-Ticket | Bình | 06/12–07/12 |
| EPIC-16 | E-Ticket | Integration Test E-Ticket | Cả hai | 08/12 |
| EPIC-17 | Cancel Booking | Thiết kế UI Cancel Booking | Đức Anh | 06/12–07/12 |
| EPIC-17 | Cancel Booking | Phát triển Cancel Booking API | Bình | 06/12–08/12 |
| EPIC-17 | Cancel Booking | Phát triển Cancel Booking Page | Đức Anh | 08/12–09/12 |
| EPIC-17 | Cancel Booking | Unit Test Cancel | Bình | 08/12–09/12 |
| EPIC-17 | Cancel Booking | Integration Test Cancel Booking | Cả hai | 10/12 |
| EPIC-18 | Dashboard | Thiết kế Dashboard UI | Đức Anh | 08/12–09/12 |
| EPIC-18 | Dashboard | Phát triển Dashboard API | Bình | 08/12–10/12 |
| EPIC-18 | Dashboard | Phát triển Dashboard Page | Đức Anh | 09/12–11/12 |
| EPIC-18 | Dashboard | Unit Test Dashboard | Bình | 10/12–11/12 |
| EPIC-18 | Dashboard | Integration Test Dashboard | Cả hai | 12/12 |
| EPIC-19 | E2E Booking & Payment | E2E Test toàn bộ flow | Cả hai | 13/12 |

# Sprint 6 — Integration, QA & Release

| Epic | Story | Task | Owner | Thời gian |
| --- | --- | --- | --- | --- |
| EPIC-19 | System Integration | Tích hợp toàn hệ thống | Cả hai | 14/12–17/12 |
| EPIC-19 | System Integration | Fix integration defects | Cả hai | 16/12–19/12 |
| EPIC-19 | Functional Testing | Functional Test | Cả hai | 18/12–21/12 |
| EPIC-19 | Security Testing | Security Test | Bình | 20/12–22/12 |
| EPIC-19 | Regression Testing | Regression Test | Cả hai | 23/12–26/12 |
| EPIC-19 | UI/UX Finalization | Review responsive UI | Đức Anh | 18/12–22/12 |
| EPIC-19 | UI/UX Finalization | UI consistency & polish | Đức Anh | 20/12–23/12 |
| EPIC-19 | Documentation | Đối chiếu implementation với tài liệu | Bình | 20/12–24/12 |
| EPIC-19 | Documentation | Cập nhật UML/ERD/FR/BR | Cả hai | 23/12–26/12 |
| EPIC-19 | Documentation | Hoàn thiện Proposal/Survey/Analysis Report | Bình | 22/12–27/12 |
| EPIC-19 | Documentation | Review định dạng và minh chứng | Đức Anh | 26/12–28/12 |
| EPIC-19 | Documentation | README + hướng dẫn setup | Bình | 24/12–28/12 |
| EPIC-19 | Documentation | Tài liệu API | Bình | 25/12–28/12 |
| EPIC-19 | Deployment & Release | Chuẩn bị môi trường Deploy | Bình | 24/12–27/12 |
| EPIC-19 | Deployment & Release | Build & cấu hình Frontend | Đức Anh | 25/12–27/12 |
| EPIC-19 | Deployment & Release | Deploy Backend + Database | Bình | 27/12–28/12 |
| EPIC-19 | Deployment & Release | Deploy Frontend | Đức Anh | 27/12–28/12 |
| EPIC-19 | Deployment & Release | Kiểm tra Backup & Migration | Bình | 28/12–29/12 |
| EPIC-19 | Deployment & Release | Smoke Test sau Deploy | Cả hai | 29/12 |
| EPIC-19 | Deployment & Release | Rehearsal Demo + Final Review | Cả hai | 29/12–30/12 |

# 4. Subtask

Không lập danh sách Subtask mặc định cho toàn bộ Task. Trong kế hoạch này, các công việc như DTO, Service, Controller, Form, Validation, API Integration, Payment record, Provider transaction ID và Gateway callback/result được giữ trong phạm vi Task tương ứng. Nếu trong quá trình triển khai một Task phát sinh khối lượng đủ lớn để cần theo dõi độc lập, nhóm có thể tạo Subtask trực tiếp trong Jira.

# 5. Quy trình thực hiện mỗi Story

Đối với feature có UI: Phân tích yêu cầu → Thiết kế UI/UX → Backend API và Frontend Page phát triển song song → Unit Test trong quá trình phát triển → API integration → Integration Test.

UI nền tảng dùng chung như Admin Layout, Header, Sidebar, Navigation và component dùng chung có thể làm sớm ở đầu Sprint 2. UI nghiệp vụ được thiết kế khi Story tương ứng bắt đầu.

# 6. Definition of Done

| Sprint | Definition of Done |
| --- | --- |
| Sprint 2 | Phase 1 core functions hoàn thành; UI/API tích hợp; Unit Test cho business logic; Integration/Smoke Test; không còn lỗi Critical ở Auth/RBAC. |
| Sprint 3 | Flight, Search, Fare và Seat Inventory hoàn thành; lifecycle/pricing rules được test; Unit + Integration Test Phase 2 đạt. |
| Sprint 4 | Passenger, Create Booking, Price Snapshot, Seat Hold và booking lifecycle hoàn thành; Unit + Integration Test đạt. |
| Sprint 5 | Payment, Retry, Confirmation, PNR, E-Ticket, Cancel và Dashboard hoàn thành; E2E Booking/Payment flow đạt. |
| Sprint 6 | Functional/Security/Regression Test hoàn thành; lỗi Critical đóng; tài liệu đồng bộ implementation; Release Candidate Deploy; Smoke Test và Demo hoàn thành. |

# 7. Scope Control

Không đưa vào kế hoạch triển khai hiện tại: Review/Rating/Comment, Refund, Online Check-in, Boarding Pass, Notification Service, Reschedule/Change Flight và Audit Log. Phase 3 có Payment nhưng không triển khai Refund flow. Customer chỉ Cancel Booking theo điều kiện đã đặc tả.

# 8. Ghi chú quản lý Jira

Epic dùng để nhóm chức năng/workstream lớn; Sprint dùng để xác định thời điểm thực hiện. Story không nên chỉ là tên entity database. Task mô tả công việc thực tế của team. Chỉ tạo Subtask khi một Task đủ lớn để cần tracking độc lập. Không sử dụng cột ghi chú Subtask trong bảng kế hoạch.